## Step2-FunctionsByCategory
|  | S3 technical body | S3 strategic level | Bottom-up body | ERDF Managing Authority | Other body responsible for complementary policy | National level* | DG REGIO - Country Desk
Strategy Design | Techno-economic analysis | [7 empty] | R= Responsible for completion
| Development and management of an effective EDP | [7 empty] | A = Accountable for decision
| Analysis of stakeholders' contributions | [7 empty] | C = consulted before action or decision
| Definition of S3 priorities | [7 empty] | I = Informed after action or decision
Identify funding sources
Create governace charter
Risk identification and risk management plan.
Monitoring S3 Strategy | Developing the conceptual model of the monitoring system
Developing the methodology to collect the data
Develop/Manage the information system for quantiative data collection
Develop/Manage the qualitative-data collection process
Implement the monitoring process (including writing the monitoring report)
Monitor quality of implementation of the monitoring system
Escalate risks emerged from the monitoring procesess to governing body
Communication and discussion of monitoring results with quadruple helix
Development of instruments | Development of instruments within ERDF
Development of instruments outside ERDF
Convert EDP outputs to Instruments
Develop integrated action plan for the strategy, associating priorities to instruments
Development of calls | Development of calls within ERDF
Development of calls outside ERDF
Definition of selection/evaluation criteria within ERDF
Definition of selection/evaluation criteria outside ERDF
Evaluation of calls within ERDF
Evaluation of calls outside ERDF
Schedule calls / ERDF
Schedule calls / non-ERDF
Transformation of EDP input to potential calls through assessment of regulatory frameworks of different funding sources (i.e. ESIF regulations, State Aid, etc.)
Stakeholder Engagement | Consultation for policy decisions
Discussion of monitoring results
General management of stakeholders' relationship
Information sessions
Create Stakeholder Engagement Plan
Monitor Stakeholder Engagement
Run EDP cycles
Discussion on new opportunities and potential synergies with other regional S3s
Monitoring ERDF OP | Definition of the monitoring indicators
Creation/management of adequate information system
Communication of ERDF Monitoring results
Establish reporting requirements
Map ERDF monitoring to S3 monitoring
Mid-Term evaluation of S3 | Setting a midterm timetable (Identifying milestones and risk assessment).
Initiating/managing the Mid-Term evaluation of S3 (this includes the technical management in the case of an external evaluator)
Defining the evaluation questions
Develop evaluation strategy/methods
Carrying out the evaluation
Communicating the evaluation results to stakeholders
Escalate risks emerged from the evaluation results
Strategy Review | Assessment of S3 implementation
Updated analysis of regional positioning/impact analysis of proposed changes
Narrowing-down/Review of priorities
Inclusion of new priorities
Mobilisation of stakeholders
Synergies with other policies | Coordination of complementary calls/investment
Information sessions
Coordination of monitoring processes
Support for stakeholders to obtain H2020 funds in S3 relevant areas
Map other policies monitoring to S3 monitoring
Development of a timeline. Synchronisation of regional, national and EU calls